## Sheet1
List of B-N | N~ of Bottleneck w/ line number | Start | Solution date | Solution Kind | VerifiedArjun | VerifiedOleg | OptimizationResult
e_Tceis | 5 from lines 850-859 | 10th Feb, 2025 | 17th Feb, 2025 | Loop Optimization, better convergence handling, Reduced redundant calculation | Yes |  | Runtime cutdown by almost 60% for overall function, no longer the heaviest function in e_Tceis
e_Tceis | Function cGamLn lines 1242-1269 | 20th Feb, 2025 | 3rd March, 2025 | Use of constexpr for Constants, avoided unnecessary precomputations in loop, Stored cx+5.5 in ctmp and used once, Uses fewer temporary variables in return statement. | Yes |  | Runtime cutdown by more than 50% for overall function, now less than chypser
e_Tceis | Function diser lines 1027-1033 | 4th March,2025 | 9th March, 2025 | Asymptotic Expansion for Large nz, Declares xz, yz, and nz as const, Simplified Conditional Structure
e_ETACHA | Function CalcOlegSum lines 1317-1331 | 10th March, 2025 | 16th March, 2025 | A single loop iterates through V, categorizing values in one pass, Uses constexpr for range values | Yes |  | The function runtime has decreased by approximately 65%
e_F4 | Function f_numPP line 673 | 17th March, 2025 | 23rd March, 2025 | Removed the unnecessary numPP variable. | Yes |  | The function runtime has decreased by approximately 29%
| Function f_numP line 636 | 20th March, 2025 | 25th March, 2025 | Removed the unnecessary numP variable. | Yes |  | Function runtime has negligible runtime compared to program runtime(Almost 95% decrease).
e_Tceis | Function digam all lines 879-884